## Inc Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (10/25/18) | Iteration 3* (11/29/18)
UC 1 | Register | 1 | 1
UC 2 | Login | 1 | 1
UC 2.1 | Forget Password | 1 | 1
UC 3 | Logout | 1 | 1
UC 4 | View Profile | 1 | 1
UC 5 | Update Profile | 1 | 1
UC 6 | View List of Vehicle(Student/Staff/non-student) | 1 | 1
UC 7 | View Inventory | 1 | 1
UC 8 | Add to Cart | 1 | 1
UC 9 | Modify/View Cart | 1 | 1
UC 10 | View List of Vehicle(Manager) | 1 | 1
UC 11 | View/Modify Vehicle Inventory | 1 | 1
UC 12 | View Vehicle Revenue | 1 | 1
UC 13 | Assign Vehicles (Row No. 15 UCID) | 1 | 1
UC 13 | Assign Location (Row No. 16 UCID) | 1 | 1
UC 13 | Assign Operator (Row No. 17 UCID) | 1 | 1
UC 13 | Assign Time Slot (Row No. 18 UCID) | 1 | 1
UC 14 | View Operator | 1 | 1
UC 15 | Modify Operator | 1 | 1
UC 16 | View Location | 1 | 1
UC 17 | Modify Location | 1 | 1
UC 18 | View/Modify Vehicle Inventory | 1 | 1
UC 19 | View Vehicle Schedule | 1 | 1
UC 20 | Checkout | 0 | 0
UC 21 | Add/Modify Card Information | 0 | 0
| Team Size | 6
Sum of the efforts of each row must not be less than the required effort
Note on C30: Robb: Enter team size here