## Inc Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (10/25/18) | Iteration 3* (11/29/18)
UC 1 | Register | 1 | 1
UC 2 | Login | 1 | 1
UC 2.1 | Forget Password | 1 | 1
UC 3 | Logout | 1 | 1
UC 4 | View Profile | 1 |  | 1
UC 5 | Update Profile | 1 |  | 1
UC 6 | View List of Vehicle(Student/Staff/non-student) | 1 |  | 1
UC 7 | View Inventory | 1 |  | 1
UC 8 | Add to Cart | 1 |  | 1
UC 9 | Modify/View Cart | 1 |  | 1
UC 10 | View List of Vehicle(Manager) | 1 |  | 1
UC 11 | View/Modify Vehicle Inventory | 1 |  | 1
UC 12 | View Vehicle Revenue | 1 |  | 1
UC 13 | Assign Vehicles(Row No. 15 UCID) | 1 |  | 1
UC 13 | Assign Location(Row No. 16 UCID) | 1 |  | 1
UC 13 | Assign Operator(Row No. 17 UCID) | 1 |  | 1
UC 13 | Assign Time Slot(Row No. 18 UCID) | 1 |  | 1
UC 14 | View Operator | 1 |  | 1
UC 15 | Modify Operator | 1 |  | 1
UC 16 | View Location | 1 |  | 1
UC 17 | Modify Location | 1 |  | 1
UC 18 | View/Modify Vehicle Inventory | 1 |  | 1
UC 19 | View Vehicle Schedule | 1 |  | 1
UC 20 | Checkout | 0 |  | 0
UC 21 | Add/Modify Card Information | 0 |  | 0
| Total Effort Estimated |  | 4 | 1
| Total Effort Available |  | 19.5 | 24
| Team Size | 6
Sum of the efforts of each row must not be less than the required effort | * Sum of the effort of each column must not exceed the ability of the team. Sum of the efforts of each row must not be less than the required effort.
Note on C30: Robb: Enter team size here